## Timeline
www.healthpolicyproject.com
Illustrative CIP Process Roadmap and Sequencing
Customize this template by changing dates, editing or adding actions, and changing due dates.
Actions | time axis 2014-09-29 to 2015-08-10
Key meetings
Project launch—in-country | bar: 2015-01-19
National FP Technical Working Group—meeting #1 | bar: 2015-01-19
Regional—meeting #1 | bar: 2015-03-09
Regional—meeting #2 | bar: 2015-05-11
National FP Technical Working Group—meeting #2 | bar: 2015-03-16
National FP Technical Working Group—meeting #3 | bar: 2015-04-06
National FP Technical Working Group—meeting #4 | bar: 2015-06-15
Plan launch | bar: 2015-08-03
Step | Sub-activity
PLAN
Step 1: Obtain Government and Key Stakeholder Buy-in
Activity 1A: Arrive at decision to engage in the CIP process | bar: 2014-09-29
Activity 1B: Make formal request for CIP support | bar: 2014-10-06
Activity 1C: Form CIP Taskforce | bar: 2014-10-27 to 2014-11-03
Activity 1D: Secure commitment for resources for CIP development | bar: 2014-11-03 to 2014-11-17
Step 2: Detail Roadmap and Secure Resources for CIP Development
Activity 2A: Form CIP Technical Support Team (TST) | bar: 2014-12-01
Activity 2B: Develop the process roadmap | bar: 2014-12-08
Activity 2C: Identify and engage stakeholders | bar: 2014-11-17 to 2014-12-08
DEVELOP
Step 3: Conduct an FP Situational Analysis
Activity 3A: Gather information on the current FP context | bar: 2015-01-12 to 2015-02-02
Activity 3B: Conduct information review, synthesis, and analysis | bar: 2015-02-02 to 2015-02-16
Activity 3C: Prioritize issues and analyze root causes | bar: 2015-02-23 to 2015-03-02
Step 4: Detail and Describe a Technical Strategy with Sub-Activities and Timeline
Activity 4A: Set or refine the FP goal | bar: 2015-03-09
Activity 4B: Develop a results framework | bar: 2015-03-16 to 2015-03-30
Activity 4C: Estimate targets | bar: 2015-04-06 to 2015-04-13
Activity 4D: Define and schedule activities | bar: 2015-03-23 to 2015-04-13
Activity 4E: Define indicators | bar: 2015-04-20 to 2015-04-27
Activity 4F: Refine and validate plan | bar: 2015-04-13 to 2015-05-18
Activity 4G: Estimate impact | bar: 2015-05-18 to 2015-05-25
Activity 4H (optional): Align with the subnational level | bar: 2015-03-02 to 2015-03-09; 2015-05-04 to 2015-05-11; 2015-06-01 to 2015-06-08
Step 5: Estimate Resources and Costs
Activity 5A: Estimate common unit costs | bar: 2015-05-25 to 2015-06-01
Activity 5B: Input quantity of units required to achieve objectives | bar: 2015-04-13 to 2015-04-20; 2015-06-08
Activity 5C: Complete costing | bar: 2015-06-15
Activity 5D: Review costing | bar: 2015-06-22
Step 6: Identify Financing Gaps
Activity 6A: Collect information on projected funding for FP | bar: 2015-06-29 to 2015-07-13
Activity 6B: Compare projected funding levels to CIP resource requirements | bar: 2015-07-13
Activity 6C: Review the estimated funding gaps | bar: 2015-07-20 to 2015-07-27
Step 7: Secure Final Approval and Launch the Plan
Activity 7A: Review and approve the CIP | bar: 2015-07-06
Activity 7B: Develop a dissemination plan and materials | bar: 2015-06-22 to 2015-06-29
Activity 7C: Produce and print the final document | bar: 2015-07-13 to 2015-07-27
Activity 7D: Hold a launch event | bar: 2015-08-03
EXECUTE
Step 8: Set Up and Manage Institutional Arrangements for Implementation
| Activity 8A: Organize an implementation coordination mechanism | 2015-08-10: -->
| Activity 8B: Develop a subnational implementation plan | 2015-08-10: -->
| Activity 8C: Identify capacity-building and implementation support needs | 2015-08-10: -->
| Activity 8D: Develop annual joint workplans | 2015-08-10: -->
| Activity 8E: Review and revise | 2015-08-10: -->
Step 9: Design and Implement Performance Monitoring Mechanisms |  | 2015-08-10: -->
| Activity 9A: Develop a performance monitoring mechanism | 2015-08-10: -->
| Activity 9B: Design data collection tools | 2015-08-10: -->
| Activity 9C: Roll out the performance monitoring system | 2015-08-10: -->
Step 10: Develop and Implement a Resource Mobilization Plan |  | 2015-08-10: -->
| Activity 10A: Develop and implement a resource mobilization plan | 2015-08-10: -->
| Activity 10B: Conduct ongoing advocacy | 2015-08-10: -->