## Slide 1: District Health Planning Developing Logical Frameworks
Rafay Eajaz Hussain
December 5, 2011

## Slide 2: Defining a systems approach
All the activities put together in an integrated way as part of a single whole.
Establish linkages in synergy
Types of fragmentation requiring integration:
  Between different objectives of the health sector
  Between different levels of the health sector
  Between different players
  Between different activities, outputs, and outcomes
Notes: Facilitator to hyperlink with the system slides from previous presentation. Facilitator to reiterate the systems approach.

## Slide 3: Types of activities
Infrastructure creation
Administrative action
Capability building
Service delivery
Community mobilisation, participation
Behaviour change communication
Supervision, support, leadership
Notes: Administrative action
  Workforce management
  Financial management
  Logistics management

## Slide 4: The District Planning Logical Framework (Log frame)
How to read a log frame

## Slide 5: What is a logical framework?
Deciding what to do
Checking what has been done
Remembering what to do
First used by the Netherlands army
Now used by many companies and government departments
Used for

## Slide 6
Purpose/ Outcome | Object/Output | Activities/ Input | Object/Output Indicators (Means of Verification (MoVs) in italics) | Activity Objectively Verifiable Indicators (OVI) and MOVs (MOVs in italics)
1. Reduction in maternal mortality. | 1.1 Increase in institutional delivery. 1.2 Access to functional Emergency Obstetric Care centres (EmOBCs). | 1. Training of ANMs in skilled birth assistance. 2. Contracting out ambulance services to NGOs. 3. Multi-skilling medical officers on emergency skills. | 1. Percent of deliveries that were institutional. No. of deliveries conducted as per facility records 2. Number of mothers who used NGO-run emergency transport system. Ambulance register and its monthly reports 3. Number of functional Emergency Obstetric Care centres. Facility records | ANMs and nurses trained for skilled birth assistance. Number of ANMs trained and training evaluation reports Number of MOUs signed with NGOs for ambulance services and ambulances. Signed MOUs Number of medical officers certified as having acquired skills. Evaluation reports
Notes: Facilitator to elaborate on the difference between the GOAL and the PURPOSE, so that there is no confusion between the two. Facilitator also to highlight the link from the slide on indicator from previous presentation (to let participants know that OVI is another name for indicator).
Other Abbreviations:
ANM= auxiliary nurse midwife
MOU = memorandum of understanding

## Slide 7: Logical framework
an Input/ Activity (column 4)
produces an Output (column 2)
which serves as an Outcome (column1)

## Slide 8: Logical framework
One outcome depends on many activities
which serves a purpose
Reduce maternal mortality and neonatal mortality (column 1)
Prioritise Institutional Deliveries
(column 2)
Training of ANMs
Arranging for transport
BCC to promote acceptance
Notes: BCC = behavioural change communication

## Slide 9: Logical framework
Achieving one purpose requires several outputs
Reduction of maternal mortality (column 1)
Increased institutional delivery (column 2)
Functional emergency obstetric care centres (column 2)

## Slide 10: An illustration
Steps of planning | Indicators
Goal: Improving child health and accelerating child survival | Impact Indicator: Reduction in infant mortality rate (IMR)
Objectives: Reduction in child malnutrition from present 52% level to below 25% in one-year timeframe To cover 100% below poverty level (BPL) families with children below 3 years of age | Outcome indicator: % of children underweight (wt. for age) % of children stunting (ht. for age) % children wasting % of anaemic children

## Slide 11: An illustration (contd.)
Strategies: Increased effectiveness & utilisation of ICDS programme Improved child feeding practices– better breastfeeding practices/complementary feeding/IYCF Micronutrient supplementation–iron, Vit. A Nutrition rehabilitation centre/medical care for Grades 3 & 4 malnutrition cases Sensitisation/training of doctors & nurses on Standard Treatment Guidelines (STGs) for managing malnutrition | Output indicator: % of children utilising ICDS (ages 0–5) % of children for whom breastfeeding initiated within 1 hr. (2 hr., 24 hr.) % of children who received exclusive breastfeeding until 6 months % of children who received paediatric iron supplement/Vit. A % of children who received deworming drugs % of children Grades 3 & 4 who received medical check-up % of doctors & nurses sensitised/ trained on STGs
Notes: ICDS = integrated child development services
IYCF = infant and young child feeding

## Slide 12: An illustration (contd.)
Increased effectiveness & utilisation of ICDS programme Activities Monthly meetings with ICDS Social mobilisation activities – community-level meetings, cultural programmes Strengthening of community-led processes – village-level meetings, monitoring and support to AWC Training of ICDS and health outreach workers Referral of Grade 3 and 4 children | Process indicators No. of meetings held and no. of follow-ups taken No., type, frequency, and location of BCC activities undertaken No. of VHSC/Mothers Groups formed, meetings, issues taken, household visits made No. and types of trainings organised No. of cases reported and referred
Notes: Abbreviations:
AWC = Ayurvedic wellness counsellor
HH = ??
VHSC = Village Health and Sanitation Committee

## Slide 13: Uses of logical framework
  Defines the tasks of the monitoring and evaluation team
  Defines the progress reports to be submitted by various officers allotted different tasks, as well as the officers in charge of the DPMU
  Forms the basis of interim and end-term evaluation
  Helps negotiate for funding with the source of funding and for approval of alterations in approved funding patterns
Notes: DPMU = district programme management unit

## Slide 14: Exercise
Take examples of previous session
Express them as a logical framework

## Slide 15: Thank You!
www.healthpolicyproject.com
The Health Policy Project is a five-year cooperative agreement funded by the U.S. Agency for International Development (USAID) under Cooperative Agreement No. AID-OAA-A-10-00067, beginning September 30, 2010. It is implemented by Futures Group, the Centre for Development and Population Activities (CEDPA), Futures Institute, Partners in Population and Development Africa Regional Office (PPD ARO), Population Reference Bureau (PRB), Research Triangle Institute (RTI) International, and the White Ribbon Alliance for Safe Motherhood (WRA).