## Slide 1: Strategic Health Action Planning An Overview of Technical Concepts
Rafay Eajaz Hussain
December 5, 2011

## Slide 2: Session objectives
To learn:
  Structuring of a plan
  Framing of objectives
  Defining outcomes, outputs, and activities
  Defining indicators
  Determining and integrating all the above and using them to make a district health plan

## Slide 3: Getting to Goals: Overview of Concepts in Planning

## Slide 4: Planning and managing a district
Requires:
  Knowing the Goals
  Knowing the Situation
  Knowing/deciding the Objectives
  Deciding the Strategies and Activities
  Relating and linking the activities to Fund Availability/Costs and Time Schedules

## Slide 5: Planning and managing a district
Requires:
  Building capacities and learning how to conduct activities
  Monitoring, assessing, and reporting the progress and constraints
  Building institutional structures
  Evaluating the programme (were the objectives met?)

## Slide 6: Different levels of planning
Goals
Impact indicators
Objectives
Outcome indicators
Strategies
Output indicators
Activities/Processes
Inputs
Process indicators
Input indicators

## Slide 7: Setting goals
What is a goal?
Societal in nature
Not necessarily measurable
Flow from vision document and societal goals
Flow from situational analysis
Responsive to people’s needs and demands
Notes: Societal in nature:
Not necessarily measurable.
Flow from vision document and societal goals—as well as from situation analysis.
Responsive to people’s needs and demands—as articulated through their representatives—the political process—and directly by different sections. This is the basis of democratic functioning.
Example: Goals in reproductive and child health (RCH) (purpose).

## Slide 8: Reproductive and child health (RCH)
RCH Goals
Better child health
Better women's health
Population stabilisation
Equity in care (does it lead to poverty reduction?)

## Slide 9: NRHM goals
Reduction in child and maternal mortality
Universal access to public services for food and nutrition, sanitation and hygiene
  universal access to public healthcare services
  emphasis on addressing women’s and children’s health and universal immunisation
Prevention and control of communicable and non-communicable diseases/locally endemic diseases
Notes: NRHM = National Rural Health Mission

## Slide 10: NRHM goals
Access to integrated comprehensive primary healthcare
Population stabilisation, gender and demographic balance
Revitalisation of local health traditions and mainstreaming AYUSH
Promotion of healthy lifestyles
Notes: AYUSH = Ayurveda, Yoga & Naturopathy, Unani, Siddha and Homoeopathy

## Slide 11: Defining objectives
What are objectives?
Relate to a programme
Decided based on goals and situation analysis
More clearly defined—are time bound
Notes: The objectives relate to a programme:
The objective are decided based on goals and…
….based on situation analysis. (The programme is what we do now to move towards the goal from where we are situated now.)
More clearly defined—in terms of time-bound character.

## Slide 12: Outcomes
Objectives defining “What would have been achieved by the end of the time period.”
Notes: Outcomes: Objectives expressed in language of “What would have been achieved by end of the time period.”

## Slide 13: Making objectives and outcomes ‘SMART’
S—SPECIFIC: Everyone should interpret it the same way.
M—MEASURABLE: An objective as different from a goal is clearly measurable.
A—APPROPRIATE: It should relate directly to the programme.
R—REALISTIC: It should be possible to achieve this objective.
T—TIME BOUND: It should be possible to achieve this within the stated timeframe.

## Slide 14: Situation analysis
Where do we stand with respect to our goals—health status indicators?
What are the outcomes of strategies to achieve these goals?
What are the constraints in implementing these strategies?
What is the status of human resources, infrastructure, etc.
Quality standards and issues.

## Slide 15: Achieving objectives
Choice of strategies to achieve the objectives
Are these strategies:
  Technically sound?
  Feasible with respect to capability and manpower?
  Feasible with respect to budget?
  Geared to manage the identified constraints?

## Slide 16: Child survival strategies
What are the possible strategies?
How does one choose between them?
  Evidence based
  Context/situation based
  Resource based
Can one avoid choosing between them? Is it enough to focus on one or two strategies?

## Slide 17: Indicators
Observable measures of how well we are doing with respect to a specific criterion—such as quality, effectiveness of the programme—against the expected objective.
Essential for monitoring and evaluation—and therefore for planning too.
Can indicators be achieved without achieving objectives?

## Slide 18: Indicator characteristics
VALID : Measures what it is supposed to measure
REPLICABLE : Gives the same result each time it is measured
PRECISE : Closest to the “truth”
SENSITIVE : Shows small differences
SPECIFIC : Relates only to what is being observed
FEASIBLE : Simple to collect and analyze

## Slide 19: Types of indicators
Impact indicators : Measure at the societal level
Outcome indicators: Measure the progress on objectives
Output indicators : Measure contribution of specific strategies
Process indicators : Measure activities
Input indicators: Measure what has gone into the programme
Notes: (Example to discuss—accredited social health activist (ASHA) programme)

## Slide 20: District Health Planning
Thematic areas

## Slide 21: Thematic areas 1 & 2: Health Systems
Providing quality services in health facilities
  Strengthening sub-centre functioning
  Primary health centres
  Achieving IPHS norms in service delivery for CHCs
  District hospitals
Support systems to health facility functioning
  Referral transport systems
  HMIS
  Procurement and logistics management for drugs and supplies
  Addressing equipment gaps in above areas
  Addressing infrastructure gaps in above areas
Notes: CHC = community health centre
HMIS = health management information systems
IPHS = Indian Public Health Standards

## Slide 22: Thematic areas 3 to 8: Health Systems
Community participation initiatives
  ASHA Programmes
  Capacity building for Panchayats and for local village planning
  Other community initiatives.
Behaviour change communication(BCC) programmes
Training activities
Addressing human resource availability and management issues
District- and block-level management for all above areas
Sector reform—governance issues
Notes: BCC programmes: (may be written along with various programme components—with a summary of all of it over here).

## Slide 23: Thematic areas: Health programmes—RCH programme
Focus areas:
  Reduction of maternal mortality
  Other women’s health issues
  Child health issues
  Immunisation, including Pulse Polio
  Population stabilisation

## Slide 24: Thematic areas: Health Programmes—Disease control programmes
Tuberculosis (RNTCP)
Vector-borne disease control (NVBDCP)
HIV control programmes
Leprosy control programmes
Other locally identified disease control priorities, including non-communicable diseases
Epidemic Response Systems
Disease Surveillance Programme
Notes: NVBDCP = National Vector-borne Disease Control Programme
RNTCP = Revised National Tuberculosis Control Programme

## Slide 25: Thematic areas: Convergent areas
Special programmes for urban areas
Special programmes for tribal populations
Special programmes for other vulnerable groups
Nutrition and food supply Issues—with emphasis on ICDS services
Water and sanitation programmes
School health programmes
Notes: ICDS = integrated child development services

## Slide 26: Thematic areas: Cross-cutting issues
Gender and equity issues
Private sector interventions
Technical assistance requirements and other inputs
Further research studies/evaluation
Notes: Gender and equity issues would be a part of each component—but a separate discussion at the end of each section is desirable.
Private sector interventions: This would also be a part of each chapter—but this also needs to be addressed as a separate component that summarises the involvement in various components, spells out general measures—separate section—especially as regarding certain functions of regulation.
Technical assistance requirements and other inputs needed from outside the district may also be summarised as a separate component.
Further research studies/evaluation needed.

## Slide 27: District Health Planning
Components of a district plan

## Slide 28: District plan components
The setting
Situational analysis
Goals and objectives
Strategies
Activities
Work plan/schedule
Monitoring and evaluation
Budget

## Slide 29: Group exercises
For each of the situations given in the work sheet
Define the following:
Goals and Impact indicators
Objectives and Outcome indicators
Strategies and Output indicators
Activities and Process indicators
Inputs and Input indicators

## Slide 30: Evaluating the group exercises
Is the Goal appropriate?
Are the Objectives/Outcomes SMART?
Are the Strategies technically sound/feasible/ contextual?
Are the Output Indicators related to strategies?
Are the Activities appropriate? Adequate?
Are the Indicators observable/verifiable?
Are Means of Verification spelt out? Technically sound as indicators?

## Slide 31
Steps of planning |  | Indicators
Goals |  | Impact Indicators
Objective/Outcomes |  | Outcome Indicators
Strategies |  | Output Indicators
Activities/Processes |  | Process Indicators
Inputs |  | Input Indicators

## Slide 32: Thank You!
www.healthpolicyproject.com
The Health Policy Project is a five-year cooperative agreement funded by the U.S. Agency for International Development (USAID) under Cooperative Agreement No. AID-OAA-A-10-00067, beginning September 30, 2010. It is implemented by Futures Group, the Centre for Development and Population Activities (CEDPA), Futures Institute, Partners in Population and Development Africa Regional Office (PPD ARO), Population Reference Bureau (PRB), Research Triangle Institute (RTI) International, and the White Ribbon Alliance for Safe Motherhood (WRA).